## P1R2DE
Formatted ID | ALMID | SNOW ID | Name | Priority | State
DE4157 |  |  | gsdsysnsap: 11.2.2.1: Getting different currency for trading price and level 1 approval offset | 2 - Medium | In Progress
DE4352 |  |  | User Vendavosystem can see data ROBUST in 5.2.1 Brands to Portfolio / Asset Manager Assignment but the same data is not available in 5.1.5.1 Country and Zone SKU Assignment | 2 - Medium | In Progress
DE4398 |  |  | Error found in US659: [Current] PM-9.9.10-SD Price list view - Not load values from 9.9.4. | 2 - Medium | Awaiting test
DE4404 | 423 |  | Even though Relevance not set, Product is available in the 9.5.1 Standard SKU Override dropdown | 2 - Medium | In Progress
DE4418 |  |  | Error found during regression: IST_P1: 11.3.1 workbook getting submitted even if pocket minimum floor is greater than trading price. | 2 - Medium | Open
DE4427 |  |  | Error found during Regression:IST_P1:"Minimum contribution Net sales" Filter is not working properly for worksheet 5.3.2.1 | 2 - Medium | In Progress
DE3768 |  |  | Staging area - missing unique index in staging tables | 2 - Medium | Awaiting test
DE4015 |  |  | 6.3.1 - Expected Market Share not defaulted to Current Market Share | 2 - Medium | In Progress
DE4074 |  |  | Sharepoint CSV - CU - Different items count in GIT and Sharepoint | 2 - Medium | In Progress
DE4142 | 296 |  | [NA UAT] Need Change in calculation of Total Market Share from Brand level to Manufacturer level for Syngenta irrespective of assigned Pricing Logic | 2 - Medium | Open
DE4160 | 311 |  | [NA Rollout] Price Adjustment % on Tail Pricing | 2 - Medium | Awaiting test
DE4163 |  |  | US1309: [Current] PM-11.2.2.1 Pocket Price Corridor Approval Level Setting - star level showing different values | 2 - Medium | In Progress
DE4197 | 325 |  | [NA Rollout] 6.3.9 - Revus UOM displayed in US imperial | 2 - Medium | In Progress
DE4198 | 324 |  | [NA Rollout] 6.3.8 - Zone Adjustment - unable to see list price for Agri-Mek (NPI logic) | 2 - Medium | Awaiting test
DE4247 |  |  | PM-10.2.1-SD Seeds Price Setting Report - wrong columns | 2 - Medium | Open
DE4264 |  |  | US310: [Current] PM-6.3.11-CP - CPAM - Price List View - removing columns | 2 - Medium | Open
DE4279 |  |  | SalesOfficeCUZone - Missing export adapter | 2 - Medium | Awaiting test
DE4286 |  |  | VAF Test Automation - 7.1.5 Price List View - UC AGI column missing | 2 - Medium | Awaiting test
DE4291 |  |  | Entitlement - Users unable to expire or revise policy table record if they are not the owner | 2 - Medium | Open
DE4403 | 422 |  | 5.1.5.1 Country and Zone SKU Assignment ¦ Relevance is not set for Material. | 2 - Medium | In Progress
DE4405 | 424 |  | Even we set leading zone in 5.1.5.1, we can see all leading zones and NOT just the ones that are relevant. | 2 - Medium | In Progress
DE4271 |  |  | Process_Acknowledgements - AckProcessor_RA adapter stuck | 3 - Low | Open
DE4132 | 293 |  | [NA UAT] CU EndZone dropdown menu on 5.1.2 | 3 - Low | In Progress

## P2R2DE
Formatted ID | ALMID | SNOW ID | Name | Priority | State
DE4175 |  |  | [CR] Create a change script that will set default values for Global Bricks and the Discretionary Discount Purpose | 1 - High | Awaiting test
DE4354 |  |  | Error found in TC1067: DM - Customer Agreements - Header - Independent/”Normal” soldTo deal: When Importing a new sold-to and creating a deal with it, I am getting an error | 1 - High | Reopened
DE2205 |  |  | [HP to configure shared volume] Adapter log files being removed from the scratch dir | 1 - High | Open
DE4034 |  |  | Performance/ProductMaterialDivision - adapter is very slow | 2 - Medium | Open
DE4360 | 405 |  | [BR-P2R2_Unit_Test] Wrong Text in email Notification to Approval | 2 - Medium | In Progress
DE4391 |  |  | regression R2 - CA deal was submitted with discount 252% even though there is a minimum pocket price policy in place | 2 - Medium | Open
DE3379 |  |  | [Reopened] DE: US 12 - Percentage field not displaying correctly for Portuguese Locale | 2 - Medium | Reopened
DE3949 |  |  | DE: Market List Price, Formula Adjustment and Negotiated Discount not hidden | 2 - Medium | Awaiting test
DE4292 |  |  | Regression R2 - FPD - Creation date is not changing | 2 - Medium | Awaiting test
DE4295 | 362 |  | IST_P1: Unit Testing : Getting multiple ‘Exchange Rate’ warning messages while adding CP material in Deal Guide | 2 - Medium | Awaiting test
DE4309 |  |  | Regression R2 - policy in 5.1.1.2 can be approved with wrong data if its created via COPY action | 2 - Medium | Awaiting test
DE4338 | 398 |  | [Clarification] Regression R2 - Discretionary Discount from CA (%) | 2 - Medium | Open
DE4339 |  |  | [Clarification] US2375: R2 Regression - Worst Case Scenario - All values should be shown in percentile | 2 - Medium | In Progress
DE4344 |  |  | V > SAP Integration - Opt-In's are only selected one at a time | 2 - Medium | Open
DE4347 |  |  | Regression R2 - validation for minus values for "Planned Volume Barter" and "Planned Volume Standard Sales" fields doesnt work correctly in DealGuide | 2 - Medium | Open
DE4348 |  |  | regression R2 - Localization/Portuguese issue | 2 - Medium | Open
DE4364 |  |  | US2375: R2 Regression - CT validity error message | 2 - Medium | Open
DE4369 |  |  | Regression R2-Clarification Defect on Aidan Murphy regarding to REVISE and END DATE on lineitem functionality when dealstatus=revising | 2 - Medium | Open
DE4389 | 420 |  | [BR-P2R2_Unit_Test] Priority, Stacking Group, and Stacking Level not displayed in CT Report | 2 - Medium | Open
DE4390 | 421 |  | [BR-P2R2_Unit_Test] Sales division filter displaying Sales+Material divison list | 2 - Medium | Awaiting test
DE4392 |  |  | US2375: R2 Regression - Pricing error, stack overflow error | 2 - Medium | Open
DE4400 |  |  | R2 Regression - Wrong counting of days in validity of deals | 2 - Medium | Open
DE4406 |  |  | R2 Regression - Localization - Portuguese issue | 2 - Medium | Open
DE4420 | 434 |  | [BR-P2R2_Unit_Test] Whle Revising CA, When Sales Rep add Line Item,He should get warning message regarding Fixed Price Deals applicable during the validity period | 2 - Medium | Open
DE4428 |  |  | Regression R2 - CA Notification shows that there is an existing FPD for customer but there seems to be none | 2 - Medium | Open
DE4429 |  |  | R2 Regression - FPD - it's not possible to edit Additional Discretionary Discount in New Proposal | 2 - Medium | Open
DE4337 |  |  | [Reopened] US2375: R2 Regression - Worst Case Scenario - "General" being shown as "Mandatory" | 2 - Medium | Awaiting test
DE4413 | 427 |  | [BR-P2R2_Unit_Test] In Vendavo Deal Guide, "Customer is Blocked" Flag is visible even Customer is not blocked in system | 2 - Medium | Open
DE4287 |  |  | R2 Upgrade : Sprint 30: IST_P1: Two adapters failed: ConditionTableToSourceMapping and WorkbookProcessDef | 3 - Low | In Progress
DE4355 |  |  | [Clarification] Regression R2 - Projected Pocket Price Standard Sales is not available according to US 926 | 3 - Low | Open
DE4365 |  |  | Regression R2 - REVISE CustomerAgreement Deal, it is possible to change RequestedDiscretionaryDiscount on 0% for lineItem but it should not | 3 - Low | In Progress
DE4381 |  |  | US2375: R2 Regression - Local CT - Material not filtered by SAP system | 3 - Low | Open
DE4386 |  |  | US2375: R2 Regression - Local CT - Material not found in GSAP worksheet | 3 - Low | Open
DE3987 |  |  | CustomerAgreement - there is no Global Brick field in LIne Item tab | 3 - Low | Awaiting test
DE4268 |  |  | US941: [Current] US 38 - Customer Agreement DG - Line Item details - volumes | 3 - Low | Open
DE4300 | 365 |  | IST_P1: Unit Testing : UI Issues in Mapping Bricks To Discretionary Discount Purposes folder | 3 - Low | Awaiting test
DE4303 | 367 |  | [PF17 Brazil] Rearranging 5.1.1.2's so that it matches the order of 5.1.1.1 | 3 - Low | Awaiting test
DE4356 |  |  | [Clarification] Regression R2 - DG - reference to the original FPD by renew is not available according to US 1175 | 3 - Low | Open
DE4370 |  |  | [Clarification] Regression R2 - Planned Volume | 3 - Low | Open
DE4426 |  |  | Regression R2- AccountBusinessPlan - miswording of validation | 3 - Low | Open